## Sheet1
Team Implementation Plan linked to Strategy
LPC Fit for Purpose
Objective | Task | Timescale | Lead | Employed Team Actions | Responsible
Improve attendance at meetings to increase representation and fill any vacancies | Using up to date collated contact details, send invitations to contractors for open meetings | Four weeks ahead of meeting | Management Team | Vacancy management to be outlined with immediate notification of vacancies and recruitment within 4 weeks. SK to continue to work with CCA when vacancies occur | Sandie Keall
Identify Pharmacy LPC Member for contact | Send contact details for each LPC Member to teams via Pharmoutcomes and website | Ongoing | Chief Officer | Contact details available via website – to ensure this is maintained | Sandie Keall
To develop a dynamic infrastructure to enable optimum output from members time | Actively seek to recruit new members to fill vacancies and use members skills more effectively between meetings | Ongoing | Chief Officer | To maintain business continuity via ensuring membership is continuous or replacements identified in a timely manner. | Sandie Keall
| Investigate opportunities through joint working with other LPCs, Pharmaceutical Industry, other provider partners. | Ongoing | Chief Officer | To investigate opportunities for joint working with pharmaceutical companies, third sector and other bodies ie AHSN, HEE, Phif | Jane Harvey and Lindsay Clode to identify network opportunities with pharma and third sector. Sandie Keall to liaise and provide business cases
To review strategy and objectives on a regular basis | Review at regular meetings the outcomes of tasks against timescales | Each meeting | Chair | Strategy to be reviewed monthly as well as action plan. LPC to be contacted monthly to determine progress against strategy to ensure workplan is adhered to | Jay Badenhorst
To work with PSNE to maximise income for Tees Valley Contractors | To provide representation on PSNE board of one Director and one Shareholder | Each meeting feedback | Nominated Individuals | Tees Valley services to be identified and progressed through PSNE as a contract provider as and when appropriate to support throughput of payments and operational delivery in pharmacy | Dawn Cruickshank - Director/Sandie Keall - Shareholder
Governance | Compliance workbook to be completed and new processes and ways of working to ensure compliance | Ongoing | Chief Officer | Assess performance and quality - CPE self evalation if updated, Risk Register, expenses, insurance, GBPR, Employee Appraisals | Sandie keall
Contractual
Objective | Task | Timescale | Lead | Employed Team Actions | Responsible
Long Term Conditions | Achievement of Quality Payment indicators | As and when new services are announced | Quality Manager/Service Implementation Manager | Further hands on support to be carried out face to face when details of the service are announced | Jane Harvey, Lindsay Clode
Identify a referral service in collaboration with Local Optical Committee and Local Dental Committee | Formulate LOC/LDC/LMC/LPC | 2024-11-01 | Chief Officer | Idenficiation of key individuals within each orgaisation to be carried out and contact made | Sandie Keall
collaborative Meeting to discuss signposting and referral options
Regional Services | PSNE ran services to be promoted and utilised in community pharmacy | Ongoing |  | To work with PSNE to identify opportunities to utilise service | Sandie Keall - to work with PSNE on service sign ups. Lindsay Clode and Jane Harvey to continue to promote and encourage pharamcies to use the service. Lindsay Clode to formulate FAQ doc to support use of the scheme
Discharge services including Discharge Medicines Service and Advanced Stop Smoking Services | To identify and establish a process for referrals from hospital to community | 2024-07-01 | Chief Officer | Local pharmacist leads in hospital and other advocates of the service via the pharmacy discharge teams to be established then further work to re-establish the service | Sandie Keall
Technology
Objective | Task | Timescale | Lead | Employed Team Actions | Responsible
To maximise meeting time by utilising technology where appropriate | To ensure the LPC has access to Microsoft Teams and Zoom and use these effectively to reduce travel time and maximise prep time and meeting. This will also have an impact on finances due to reduced travel time. | Ongoing | Chief Officer | To ensure that team meetings are planned with alternate LPC meetings booked as online only. To where possible and appropriate meet with commissioners and other bodies electronically to reduce costs. | Sandie Keall
To ensure equipment to support new services is available where possible via the LPC | To procure the 'best deal' for contractors on equipment to support service delivery | Ongong | Chief Officer | SK to liaise with providers of medical equipment to identify opportunities for discounted costs or utilisation of non Levy funds to purchase where possible | Sandie Keall
Workforce Capability and Training
Objective | Task | Timescale | Lead | Employed Team Actions | Responsible
To share best practice | To formulate case studies and best practice documents and share across the area | Quartely in newsletter | Quality Manager | To work with LPC members and managers to identify opportunities for highlighting best practice and cirulate via newsletter and website | Lindsay Clode
|  |  | Service Implementation and Peer Support Manager | To work with teams to identify areas of best practice for highlighting particularly around health promotion and prevention | Jane Harvey
Encourage Training | Inform contractors of any training that is available via the website and newsletter | Ongoing | Training Manager | Provision of a variety of opportunities to include: | Lindsay Clode to formulate and keep up to date training plan on both website and to regularly update contractors
Mental Health Training
Flu Training
New service training
Maximise the use of Virtual outcomes
| To formulate case studies and best practice documents and share across the area |  |  | To work with LPC members and managers to identify opportunities for highlighting best practice and circulate via newsletter and website | Lindsay Clode
|  |  |  | To work with teams to identify areas of best practice for highlighting particularly around health promotion and prevention | Jane Harvey
Long Term Conditions in Pharmacy utilising the entire team | Hypertension Case Finding Service | 2024-04-01 | Sandie Keall and Lindsay Clode | To review national training requirements and SLA to provide the service. To formulate specific news update with key points and requirements for contractors. | Sandie Keall to liaise with NHSE and Place Leads regarding referral pathways Lindsay Clode to formulate key points document and training updates
| Diabetes review seven point plan of care to be formulated and presented toPlace Leads |  | Sandie Keall | Diabetes training package to be reviewed to determine costings and feasibility. Funding to be sought to ensure it is free to deliver to pharmacy teams | Sandie Keall - to liaise with PCN pharmacist with a special interest
| Asthma review service | 2024-12-01 | Sandie Keall | Local pilot service with Mike Maguire regarding inhaler technique and environmental concerns to conclude January 2024 | Sandie Keall
| – annual review extending Quality Payment indicator |  | Sandie Keall | Further hands on support to be carried out face to face when payment structure revealed | Jane Harvey, Lindsay Clode
| Launch of UTI PGD servce |  | Sandie Keall | To determine the collaboration between national Common Conditions service and ICB services | Sandie Keall to promote the service once implemented including sign ups.
GPCPCS | To identify opportunities for referral pathways and provide an education forum for training GP staff on appropriate | Ongoing | Sandie Keall | GP Training to be carried out where appropriate to ensure they have an understanding of the process for appropriate referrals. | Sandie Keall
| Pharmacy team promotion of the service with timely management of referrals |  |  | Lindsay Clode and Jane Harvey to review referrals daily when information available and contact pharmacies with outstanding referrals. Training where appropriate | Lindsay Clode and Jane Harvey
Conmmunications
Objective | Task | Timescale | Lead | Employed Team Actions | Responsible
Regular communication with all contractors | LPC to send contractors a newsletter informing members of current issues, updates and information. summary email to be sent via Pharmoutcomes and Facebook with links to news stories and information | Monthly | Management Team | Overview to LPC with dissemination via all appropriate methods. Facebook, Pharmoutcomes, website. Paper copies only if requested | Sandie Keall
Jane Harvey
Lindsay Clode
Update LPC website regularly | Articles notifying contractors of news affecting pharmacy | Ongoing | Chief Officer | Website has been redesigned. This now has 3 distinct areas for pharmacy, Healthcare professionals and patients | Sandie Keall
Jane Harvey – local services area and patient area
Lindsay Clode – training and national services and healthcare professionals area
Improve attendance at meetings to increase representation and fill any vacancies | Using up to date collated contact details, send invitations to contractors for open meetings | Four weeks ahead of meeting | Management Team | Vacancy management to be outlined with immediate notification of vacancies and recruitment within 4 weeks. SK to continue to work with CCA when vacancies occur | Sandie Keall
Regular communication with all contractors | LPC to send contractors a newsletter informing members of current issues, updates and information. summary email to be sent via | Monthly | Management Team | Overview to LPC with dissemination via all appropriate methods. Facebook, Pharmoutcomes, website. Paper copies only if requested | Sandie Keall
Jane Harvey
Lindsay Clode
Update LPC website regularly | Articles notifying contractors of news affecting pharmacy | Ongoing | Chief Officer | Website has been redesigned. This now has 3 distinct areas for pharmacy, Healthcare professionals and patients | Sandie Keall
Jane Harvey – local services area and patient area
Lindsay Clode – training and national services and healthcare professionals area